## Release Plan
Increment Plan
Incr. | Start | Days | End | Size | Status | Release Date | Goal
1 | 2022-11-19 | 84 | 2023-02-10 | 95
2 | 2023-02-11 | 0 | 2023-02-10
Template note: Increment plan is intended to collect individual sprints into larger releases. In smaller projects, this is not needed.
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2022-11-19 | 14 | 2022-12-02 | 15 | Released | 2022-12-02 | meeting | 1
2 | 2022-12-03 | 14 | 2022-12-16 | 16 | Released | 2022-12-16 | thai leag (Ul) | 1
3 | 2022-12-17 | 14 | 2022-12-30 | 16 | Released | 2022-12-30 | Editl thai leag (Ul) | 1
4 | 2022-12-31 | 14 | 2023-01-13 | 24 | Released | 2023-01-13 | Research | 1
5 | 2023-01-14 | 14 | 2023-01-27 | 19 | Released | 2023-01-27 | NEW thai leag (Ul) | 1
6 | 2023-01-28 | 14 | 2023-02-10 | 5 | Released | 2023-02-10 | Usability test, documentation, prototype corrections | 1
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | 0
Formulas:
Start = IF(OR(B16="",[Incr.]=""),"",B16)
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")
Release Date = [End]

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Comments
1 | find information Thai Leage | Done | 6 | 5
2 | meeting Thai Leage | Done | 4 | 5
3 | logo Thai Leage | Done | 2 | 2
4 | design Thai Leage | Done | 3 | 3
5 | main page ux/ui | Done | 7 | 8
6 | Login ux/ui | Done | 5 | 3
7 | Main all ux/ui | Done | 4 | 2
8 | football news all ux/ui | Done | 6 | 7
9 | setting ux/ui | Done | 7 | 6
10 | modify main page ux/ui | Done | 3 | 4
11 | club information | Done | 8 | 6
12 | modify meeting | Done | 4 | 5
13 | input main page ux/ui | Done | 3 | 3
14 | privacy policy ux/ui | Done | 5 | 6
15 | Terms of Service | Done | 4 | 3
16 | Terms of Service | Done | 6 | 5
17 | Community Guidelines | Done | 4 | 3
18 | copyright Thai Leage | Done | 2 | 4
19 | open sensors | Done | 7 | 6
20 | Program Framework | Done | 5 | 5
Sort Product Backlog
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 95 |  | Sprint count | 7
Count trend from last |  |  | 91 | sprints | Trend sprint count | 1
[5 empty] | Trend offset | 0 | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 1 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 30 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
91 | [15 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  |  |  | Trend count | 1 | [9 empty] | (i.e. if the amount of story points
Average last 8 | [15 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 | [15 empty] | of the bars indicate the estimated size of the project at the
Trend | [15 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 2
Original estimate - Avg |  |  | 4
Original estimate - Max |  |  | 6 |  | Standard Dev. | 1
91
Realized average |  |  |  |  | LastPlanned | 3
Average last 8 |  |  |  |  | LastRealized | 1
Avg. worst 3 in last 8
Trend
Realized + St. Dev
Realized - St. Dev
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 91 | 15 |  | 91 | 91 | 91 | 0 | 0 | 91 | 91 | 91 | 0
2 | 76 | 13 |  | 91 | 0 | 0 | 76 | 76 | 76 | 91 |  | 0
3 | 63 | 14 |  | 91 | 0 | 0 | 63 | 63 | 63 | 91 |  | 0
4 | 49 | 23 |  | 91 | 0 | 0 | 49 | 49 | 49 | 91 |  | 0
5 | 26 | 18 |  | 91 | 0 | 0 | 26 | 26 | 26 | 91 |  | 0
6 | 8 | 5 |  | 91 | 0 | 0 | 8 | 8 | 8 | 91 |  | 0
7 | 3 |  |  | 91 | 0 | 0 | 3 | 3 | 3 | 91 |  | 0
8 | [9 empty] | 91 |  | 0
9 | [9 empty] | 91 |  | 0
10 | [9 empty] | 91 |  | 0
11 | [9 empty] | 91 |  | 0
12 | [9 empty] | 91 |  | 0
13 | [9 empty] | 91 |  | 0
14 | [9 empty] | 91 |  | 0
15 | [9 empty] | 91 |  | 0
16 | [9 empty] | 91 |  | 0
17 | [9 empty] | 91 |  | 0
18 | [9 empty] | 91 |  | 0
19 | [9 empty] | 91 |  | 0
20 | [9 empty] | 91 |  | 0
21 | [9 empty] | 91 |  | 0
22 | [9 empty] | 91 |  | 0
23 | [9 empty] | 91 |  | 0
24 | [9 empty] | 91 |  | 0
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate

## Sp1
1
Sprint implementation days | 10 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 10 | Days | Totals | 30 | 28 | 25 | 21 | 18 | 15 | 11 | 7 | 3 | 1 | 0
Task rows | 4 | Done days | 9 |  | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3
Warning! These are necessary |  | Trend |  |  | 28.2667 | 24.7833 | 21.3 | 17.8167 | 14.3333 | 10.85 | 7.3667 | 3.8833 | 0.4
template rows |  | Trend Days | 9 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 28.2667 1: 1; 24.7833 2: 2; 21.3 3: 3; 17.8167 4: 4; 14.3333 5: 5; 10.85 6: 6; 7.3667 7: 7; 3.8833 8: 8; 0.4 9: 9; 0.4 10: 10
find information Thai Leage | 1 | scrum team | Done | 6 | 28.2667 1: 6; 24.7833 2: 3; 21.3 3: 2; 17.8167 4: 1
meeting Thai Leage | 2 | scrum team | Done | 8 | 28.2667 1: 8; 24.7833 2: 6; 21.3 3: 4; 17.8167 4: 3; 14.3333 5: 1
logo Thai Leage | 3 | ux ui designer Bam | Done | 10 | 28.2667 1: 10; 24.7833 2: 9; 21.3 3: 9; 17.8167 4: 9; 14.3333 5: 6; 10.85 6: 3; 7.3667 7: 2; 3.8833 8: 1
design Thai Leage | 4 | ux ui designer Bam | Done | 10 | 28.2667 1: 10; 24.7833 2: 9; 21.3 3: 9; 17.8167 4: 9; 14.3333 5: 7; 10.85 6: 5; 7.3667 7: 3; 3.8833 8: 1
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2
1
Sprint implementation days | 10 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 10 | Days | Totals | 31 | 29 | 28 | 26 | 23 | 20 | 19 | 16 | 15 | 8 | 5 | 2 | 1
Task rows | 3 | Done days | 12 |  | 31 | 27.9 | 31 | 27.9 | 24.8 | 21.7 | 18.6 | 15.5 | 12.4 | 9.3 | 6.2 | 3.1
Warning! These are necessary |  | Trend |  |  | 32.4485 | 29.5333 | 26.6182 | 23.703 | 20.7879 | 17.8727 | 14.9576 | 12.0424 | 9.1273 | 6.2121 | 3.297 | 0.38182
template rows |  | Trend Days | 10 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 1; 4: 2; 5: 3; 6: 4; 7: 5; 8: 6; 9: 7; 10: 8; 11: 9; 12: 10
main page ux/ui | 5 | Developer tee | Done | 10 | 1: 9; 2: 8; 3: 8; 4: 5; 5: 3; 6: 2; 7: 1
Login ux/ui | 6 | Project manage ken | Done | 10 | 1: 10; 2: 7; 3: 4; 4: 2; 5: 1
Main all ux/ui | 7 | Project manage ken | Done | 10 | 1: 10; 2: 8; 3: 6; 4: 5; 5: 3; 6: 1
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp3
1
Sprint implementation days | 10 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 10 | Days | Totals | 27 | 19 | 14 | 12 | 10 | 7 | 6 | 4 | 3 | 2 | 1
Task rows | 5 | Done days | 10 |  | 27 | 24.3 | 21.6 | 18.9 | 16.2 | 13.5 | 10.8 | 8.1 | 5.4 | 2.7
Warning! These are necessary |  | Trend |  |  | 16.2545 | 14.3758 | 12.497 | 10.6182 | 8.7394 | 6.8606 | 4.9818 | 3.103 | 1.2242
template rows |  | Trend Days | 10 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 16.2545 1: 1; 14.3758 2: 2; 12.497 3: 3; 10.6182 4: 4; 8.7394 5: 5; 6.8606 6: 6; 4.9818 7: 7; 3.103 8: 8; 1.2242 9: 9; 1.2242 10: 10
football news all ux/ui | 8 | Developer tawam | Done | 5 | 16.2545 1: 3; 14.3758 2: 2; 12.497 3: 3
football news all ux/ui | 8 | Developer tee | Done | 5 | 16.2545 1: 1; 14.3758 2: 2; 12.497 3: 3; 10.6182 4: 4
setting ux/ui | 9 | Developer tawam | Done | 5 | 16.2545 1: 5; 14.3758 2: 5; 12.497 3: 5; 10.6182 4: 5
setting ux/ui | 9 | Developer tee | Done | 5 | 16.2545 1: 5; 14.3758 2: 5; 12.497 3: 5; 10.6182 4: 5
modify main page ux/ui | 10 | Developer tawam | Done | 5 | 16.2545 1: 5
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp4
1
Sprint implementation days | 10 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 10 | Days | Totals | 52 | 30 | 28 | 24 | 21 | 18 | 15 | 13 | 7 | 5 | 2
Task rows | 7 | Done days | 10 |  | 52 | 46.8 | 41.6 | 36.4 | 31.2 | 26 | 20.8 | 15.6 | 10.4 | 5.2
Warning! These are necessary |  | Trend |  |  | 30.6182 | 27.4364 | 24.2545 | 21.0727 | 17.8909 | 14.7091 | 11.5273 | 8.3455 | 5.1636 | 1.9818
template rows |  | Trend Days | 10 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 30.6182 1: 1; 27.4364 2: 2; 24.2545 3: 3; 21.0727 4: 4; 17.8909 5: 5; 14.7091 6: 6; 11.5273 7: 7; 8.3455 8: 8; 5.1636 9: 9; 1.9818 10: 10
Include club information | 11 | ux ui designer Bam | Done | 5 | 30.6182 1: 5; 27.4364 2: 2; 24.2545 3: 0
club information | 12 | ux ui designer Bam | Done | 7 | 30.6182 1: 7; 27.4364 2: 7; 24.2545 3: 2; 21.0727 4: 2
modify meeting | 13 | ux ui designer Bam | Done | 12 | 30.6182 1: 12; 27.4364 2: 12; 24.2545 3: 12; 21.0727 4: 10
input main page ux/ui | 14 | Developer tawam | Done | 8 | 30.6182 1: 8; 27.4364 2: 6; 24.2545 3: 4; 21.0727 4: 3; 17.8909 5: 1
input main page ux/ui | 14 | Developer tee | Done | 1o | 30.6182 1: 8; 27.4364 2: 6; 24.2545 3: 4; 21.0727 4: 3; 17.8909 5: 2; 14.7091 6: 1
privacy policy ux/ui | 15 | Developer tawam | Done | 10 | 30.6182 1: 8; 27.4364 2: 6; 24.2545 3: 5; 21.0727 4: 3; 17.8909 5: 1
privacy policy ux/ui | 15 | Developer tawam | Done | 10 | 30.6182 1: 8; 27.4364 2: 6; 24.2545 3: 5; 21.0727 4: 3; 17.8909 5: 1
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp5
1
Sprint implementation days | 10 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 10 | Days | Totals | 30 | 28 | 24 | 21 | 19 | 17 | 15 | 13 | 10 | 6 | 4
Task rows | 4 | Done days | 10 |  | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3
Warning! These are necessary |  | Trend |  |  | 27.0727 | 24.5455 | 22.0182 | 19.4909 | 16.9636 | 14.4364 | 11.9091 | 9.3818 | 6.8545 | 4.3273 | 1.8
template rows |  | Trend Days | 10 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 27.0727 1: 1; 24.5455 2: 2; 22.0182 3: 3; 19.4909 4: 4; 16.9636 5: 5; 14.4364 6: 6; 11.9091 7: 7; 9.3818 8: 8; 6.8545 9: 9; 4.3273 10: 10
Terms of Service | 16 | Developer tawam | Done | 5 | 27.0727 1: 3; 24.5455 2: 2; 22.0182 3: 3; 19.4909 4: 0
Community Guidelines | 17 | Developer tee | Done | 5 | 27.0727 1: 1; 24.5455 2: 2; 22.0182 3: 3; 19.4909 4: 4
copyright Thai Leage | 18 | Developer tawam | Done | 5 | 27.0727 1: 5; 24.5455 2: 5; 22.0182 3: 5; 19.4909 4: 5
open sensors | 19 | Developer tee | Done | 5 | 27.0727 1: 5; 24.5455 2: 5; 22.0182 3: 5; 19.4909 4: 5
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp6
1
Sprint implementation days | 10 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 10 | Days | Totals | 31 | 29 | 27 | 20 | 15 | 13 | 10 | 7 | 5 | 3 | 1
Task rows | 5 | Done days | 10 |  | 31 | 27.9 | 24.8 | 21.7 | 18.6 | 15.5 | 12.4 | 9.3 | 6.2 | 3.1
Warning! These are necessary |  | Trend |  |  | 27.2364 | 24.0727 | 20.9091 | 17.7455 | 14.5818 | 11.4182 | 8.2545 | 5.0909 | 1.9273
template rows |  | Trend Days | 10 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 27.2364 1: 1; 24.0727 2: 2; 20.9091 3: 3; 17.7455 4: 4; 14.5818 5: 5; 11.4182 6: 6; 8.2545 7: 7; 5.0909 8: 8; 1.9273 9: 9; 1.9273 10: 10
Program Framework | 20 | Project manage ken | Ongoing | 10 | 27.2364 1: 6; 24.0727 2: 6; 20.9091 3: 5; 17.7455 4: 3; 14.5818 5: 2; 11.4182 6: 1
Program Framework | 20 | ux ui designer Bam | Ongoing | 10 | 27.2364 1: 8; 24.0727 2: 6; 20.9091 3: 5; 17.7455 4: 3; 14.5818 5: 2; 11.4182 6: 1
Program Framework | 20 | Developer tawam | Ongoing | 10 | 27.2364 1: 7; 24.0727 2: 6; 20.9091 3: 5; 17.7455 4: 3; 14.5818 5: 2; 11.4182 6: 1
Program Framework | 20 | Developer tee | Ongoing | 10 | 27.2364 1: 6; 24.0727 2: 4; 20.9091 3: 3; 17.7455 4: 3; 14.5818 5: 2; 11.4182 6: 1
Program Framework | 20 | Scrum master tar | Ongoing | 10 | 27.2364 1: 7; 24.0727 2: 6; 20.9091 3: 5; 17.7455 4: 3; 14.5818 5: 2; 11.4182 6: 1
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.